## 1.2.2022
[ANGELA MACHA] TASK LIST | [9 empty] | 0
[7 empty] | Budget | Est.Hours | Act.Hours
|  | Month / Year | 2022-01-02 |  |  | Totals | 0 | 0 | 0
TASK | DEPENDENCIES | PRIORITY | START | END | % COMPLETE | DONE | BUDGET | EST. HOURS | ACTUAL HOURS | NOTES
0
CHECK AND BALANCE | [5 empty] | 0
Testing the system to see if it works as expected. | Sadru | HIGH | 2022-01-02 | 2022-01-02 | 100% | 1 |  | 1.30hrs | 1.10hrs
Modification of check and balance usermanual |  | MEDIUM | 2022-01-02 | 2022-01-02 | 100% | 1 |  | 1hr | 1hr
0
0
VICOBA | [5 empty] | 0
Modifying Requirements document after receiving suggestions from the team |  | HIGH | 2022-01-02 | 2022-01-02 | 100% | 1 |  | 30min | 30min
LEARNING APP
Development of some modules in learning web application. |  | HIGH | 28/1/2022 | 28/1/2022 | 17% | 0 |  | 5hrs | 5hrs
0
Note on B5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: List of tasks / factors /. employees etc who are factor to the progress on this task

## 2.2.2022
[ANGELA MACHA] TASK LIST | [9 empty] | 0
[7 empty] | Budget | Est.Hours | Act.Hours
|  | Month / Year | 2022-02-02 |  |  | Totals | 0 | 0 | 0
TASK | DEPENDENCIES | PRIORITY | START | END | % COMPLETE | DONE | BUDGET | EST. HOURS | ACTUAL HOURS | NOTES
0
LEARNING APP | [5 empty] | 0
Learning and developing prrogramme and course module |  | HIGH | 2022-02-02 | 2022-02-02 | 20% | 0 |  | 8hrs | 8.30hrs
0
0
0
Note on B5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: List of tasks / factors /. employees etc who are factor to the progress on this task

## 3.2.2022
[ANGELA MACHA] TASK LIST | [9 empty] | 0
[7 empty] | Budget | Est.Hours | Act.Hours
|  | Month / Year | 2022-03-02 |  |  | Totals | 0 | 0 | 0
TASK | DEPENDENCIES | PRIORITY | START | END | % COMPLETE | DONE | BUDGET | EST. HOURS | ACTUAL HOURS | NOTES
0
LEARNING APP | [5 empty] | 0
developing Learning APP modules |  | HIGH | 2022-03-02 | 2022-03-02 | 25% | 0 |  | 8hrs | 7.30hrs
0
0
0
Note on B5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: List of tasks / factors /. employees etc who are factor to the progress on this task

## 4.2.2022
[ANGELA MACHA] TASK LIST | [9 empty] | 0
[7 empty] | Budget | Est.Hours | Act.Hours
|  | Month / Year | 2022-04-02 |  |  | Totals | 0 | 0 | 0
TASK | DEPENDENCIES | PRIORITY | START | END | % COMPLETE | DONE | BUDGET | EST. HOURS | ACTUAL HOURS | NOTES
0
LEARNING APP | [5 empty] | 0
developing Learning APP modules |  | HIGH | 2022-04-02 | 2022-04-02 | 27% | 0 |  | 5hrs | 3.40hrs
0
0
ENVIT SYSTEM
Embeding QR Codes in the Cards. | Team | HIGH | 2022-04-02 | 2022-04-02 | 100% | 1 |  |  | 3.47hrs
Note on B5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: List of tasks / factors /. employees etc who are factor to the progress on this task

## 7.2.2022
[ANGELA MACHA] TASK LIST | [9 empty] | 0
[7 empty] | Budget | Est.Hours | Act.Hours
|  | Month / Year | 2022-07-02 |  |  | Totals | 0 | 0 | 0
TASK | DEPENDENCIES | PRIORITY | START | END | % COMPLETE | DONE | BUDGET | EST. HOURS | ACTUAL HOURS | NOTES
0
ENVIT SYSTEM | [5 empty] | 0
Creating and sending cards to the invitees |  | HIGH | 2022-07-02 | 2022-07-02 | 100% | 1 |  |  | 8hrs
0
0
Note on B5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: List of tasks / factors /. employees etc who are factor to the progress on this task

## 8.2.2022
[ANGELA MACHA] TASK LIST | [9 empty] | 0
[7 empty] | Budget | Est.Hours | Act.Hours
|  | Month / Year | 2022-08-02 |  |  | Totals | 0 | 0 | 0
TASK | DEPENDENCIES | PRIORITY | START | END | % COMPLETE | DONE | BUDGET | EST. HOURS | ACTUAL HOURS | NOTES
0
ENVIT SYSTEM | [5 empty] | 0
Creating and sending cards to the invitees |  | HIGH | 2022-08-02 | 2022-08-02 | 100% | 1 |  |  | 8hrs
0
0
Note on B5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: List of tasks / factors /. employees etc who are factor to the progress on this task

## 9.2.2022
[ANGELA MACHA] TASK LIST | [9 empty] | 0
[7 empty] | Budget | Est.Hours | Act.Hours
|  | Month / Year | 2022-09-02 |  |  | Totals | 0 | 0 | 0
TASK | DEPENDENCIES | PRIORITY | START | END | % COMPLETE | DONE | BUDGET | EST. HOURS | ACTUAL HOURS | NOTES
0
ENVIT SYSTEM | [5 empty] | 0
Creating and sending cards to the invitees |  | HIGH | 2022-09-02 | 2022-09-02 | 100% | 1 |  |  | 2hrs
0
0
LEARNING APP
developing Learning APP modules |  | HIGH | 2022-09-02 | 2022-09-02 | 30% | 0 |  |  | 6hrs
Note on B5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: List of tasks / factors /. employees etc who are factor to the progress on this task

## 10.2.2022
0
[7 empty] | Budget | Est.Hours | Act.Hours
|  | Month / Year | 2022-10-02 |  |  | Totals | 0 | 0 | 0
TASK | DEPENDENCIES | PRIORITY | START | END | % COMPLETE | DONE | BUDGET | EST. HOURS | ACTUAL HOURS | NOTES
0
ENVIT SYSTEM | [5 empty] | 0
Creating and sending cards to the invitees |  | HIGH | 2022-10-02 | 2022-10-02 | 100% | 1 |  |  | 1hrs
0
0
LEARNING APP
developing Learning APP modules |  | HIGH | 2022-10-02 | 2022-10-02 | 33% | 0 |  |  | 7hrs
Note on B5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: List of tasks / factors /. employees etc who are factor to the progress on this task

## 11.2.2022
0
[7 empty] | Budget | Est.Hours | Act.Hours
|  | Month / Year | 2022-10-02 |  |  | Totals | 0 | 0 | 0
TASK | DEPENDENCIES | PRIORITY | START | END | % COMPLETE | DONE | BUDGET | EST. HOURS | ACTUAL HOURS | NOTES
0
CHECK AND BALANCE | [5 empty] | 0
Creating system handout |  | HIGH | 2022-11-02 | 2022-11-02 | 100% | 1 |  |  | 3hrs
0
0
DOCUMENT
Scanning document |  | HIGH | 2022-11-02 | 2022-11-02 | 100% | 1 |  |  | 20min
Binding Document |  | HIGH | 2022-11-02 | 2022-11-02 | 100% | 1 |  |  | 30min
LEARNING APP
developing Learning APP modules |  | HIGH | 2022-11-02 | 2022-11-02 | 35% |  |  |  | 5hrs
ECARD
Looking for wedding card template |  | HIGH | 2022-11-02 | 2022-11-02 | 100% | 1 |  |  | 20min
Note on B5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: List of tasks / factors /. employees etc who are factor to the progress on this task

## 14.2.2022
0
[7 empty] | Budget | Est.Hours | Act.Hours
|  | Month / Year | 14/2/2022 |  |  | Totals | 0 | 0 | 0
TASK | DEPENDENCIES | PRIORITY | START | END | % COMPLETE | DONE | BUDGET | EST. HOURS | ACTUAL HOURS | NOTES
0
CHECK AND BALANCE | [5 empty] | 0
Creating system handout |  | HIGH | 14/2/2022 | 14/2/2022 | 33% | 0 |  |  | 1hrs
0
0
BIOMETRIC SYSTEM
Studying and Initial development |  | HIGH | 14/2/2022 | 14/2/2022 | 10% | 0 |  |  | 5min
LEARNING APP
developing Learning APP modules |  | HIGH | 14/2/2022 | 14/2/2022 | 37% |  |  |  | 1.5hrs
Note on B5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: List of tasks / factors /. employees etc who are factor to the progress on this task

## 15.2.2022
0
[7 empty] | Budget | Est.Hours | Act.Hours
|  | Month / Year | 15/2/2022 |  |  | Totals | 0 | 0 | 0
TASK | DEPENDENCIES | PRIORITY | START | END | % COMPLETE | DONE | BUDGET | EST. HOURS | ACTUAL HOURS | NOTES
CHECK AND BALANCE
Updating system handout for TFF and creating other handouts for board and team. |  | HIGH | 15/2/2022 | 15/2/2022 | 100% | 1 |  |  | 2hrs 10min
BIOMETRIC SYSTEM
Proceeding with initial development |  | HIGH | 15/2/2022 | 15/2/2022 | 14% | 0 |  |  | 4hrs 40min
MEETING
Discussion about requirements from CRDB for B-Smart Academi |  | HIGH | 15/2/2022 | 15/2/2022 | 100% | 1 |  |  | 1hrs 12min
Note on B5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: List of tasks / factors /. employees etc who are factor to the progress on this task

## 16.2.2022
0
[7 empty] | Budget | Est.Hours | Act.Hours
|  | Month / Year | 2022-02-16 |  |  | Totals | 0 | 0 | 0
TASK | DEPENDENCIES | PRIORITY | START | END | % COMPLETE | DONE | BUDGET | EST. HOURS | ACTUAL HOURS | NOTES
0
CHECK AND BALANCE | [5 empty] | 0
Updating system handout |  | HIGH | 2022-02-16 | 2022-02-16 | 30% | 0 |  |  | 1.30hrs
0
0
BIOMETRIC SYSTEM
Proceeding with Initial development |  | HIGH | 2022-02-16 | 2022-02-16 | 25% | 0 |  |  | 4hrs
LEARNING APP
developing Learning APP modules |  | HIGH | 2022-02-16 | 2022-02-16 | 37% | 0 |  |  | 1.20hrs
CARD TEMPLATE
Editing Card template |  | HIGH | 2022-02-16 | 2022-02-16 | 70% | 0 |  |  | 1.27hrs
Note on B5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: List of tasks / factors /. employees etc who are factor to the progress on this task

## 17.2.2022
0
[7 empty] | Budget | Est.Hours | Act.Hours
|  | Month / Year | 17/2/2022 |  |  | Totals | 0 | 0 | 0
TASK | DEPENDENCIES | PRIORITY | START | END | % COMPLETE | DONE | BUDGET | EST. HOURS | ACTUAL HOURS | NOTES
0
CARD | [5 empty] | 0
Editing card template |  | HIGH | 2022-02-17 | 2022-02-17 | 90% | 0 |  |  | 1.30hrs
0
0
BIOMETRIC SYSTEM
Proceeding with Initial development |  | HIGH | 2022-02-16 | 2022-02-16 | 40% | 0 |  |  | 6.40hrs
Note on B5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: List of tasks / factors /. employees etc who are factor to the progress on this task

## 18.2.2022
0
[7 empty] | Budget | Est.Hours | Act.Hours
|  | Month / Year | 2022-02-18 |  |  | Totals | 0 | 0 | 0
TASK | DEPENDENCIES | PRIORITY | START | END | % COMPLETE | DONE | BUDGET | EST. HOURS | ACTUAL HOURS | NOTES
VICOBA DOCUMENT
Updating vicoba document by adding clear definition of evicoba, objectives and users. |  | HIGH | 2022-02-18 | 2022-02-18 | 70% | 0
0
0
BIOMETRIC SYSTEM
Proceeding with development |  | HIGH | 2022-02-18 | 2022-02-18 | 60% | 0 |  |  | 6.40hrs
Note on B5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: List of tasks / factors /. employees etc who are factor to the progress on this task

## 21.2.2022
0
[7 empty] | Budget | Est.Hours | Act.Hours
|  | Month / Year | 2022-02-21 |  |  | Totals | 0 | 0 | 0
TASK | DEPENDENCIES | PRIORITY | START | END | % COMPLETE | DONE | BUDGET | EST. HOURS | ACTUAL HOURS | NOTES
LEARNING APP
Developing learning app modules |  | HIGH | 2022-02-21 | 2022-02-21 | 39% | 0 |  |  | 2.30hrs
0
0
BIOMETRIC SYSTEM
Proceeding with development |  | HIGH | 2022-02-21 | 2022-02-21 | 65% | 0 |  |  | 5hrs
Note on B5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: List of tasks / factors /. employees etc who are factor to the progress on this task

## Sheet1
0
[7 empty] | Budget | Est.Hours | Act.Hours
|  | Month / Year | 2022-02-22 |  |  | Totals | 0 | 0 | 0
TASK | DEPENDENCIES | PRIORITY | START | END | % COMPLETE | DONE | BUDGET | EST. HOURS | ACTUAL HOURS | NOTES
LEARNING APP
Developing learning app modules |  | HIGH | 2022-02-22 | 2022-02-22 | 40% | 0 |  |  | 1.30hrs
0
0
BIOMETRIC SYSTEM
Proceeding with development |  | HIGH | 2022-02-22 | 2022-02-22 | 67% | 0 |  |  | 5hrs
ECARD
Discussion on the part of contribution | Patric | HIGH | 2022-02-22 | 2022-02-22 | 100% | 1 |  |  | 1.35hrs
Development of the Contribution module Interface |  | HIGH | 2022-02-22 | 2022-02-22 | 100% | 1 |  |  | 1.20hrs
Note on B5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: List of tasks / factors /. employees etc who are factor to the progress on this task